Elio

Development Roadmap

Last Updated: 27 March 2026  •  Sprint 8 (Analytics & Core Polish)

# Feature Audit Summary

## Implemented (Sprints 1–7)

- ✅ Onboarding flow (6 screens: welcome, dietary, kitchen preset, pantry review, household, style)

- ✅ Google Sign-In + Guest Mode

- ✅ Two-tier pantry (Always Have, Almost Always Have) + session perishables

- ✅ Running Low flag per item

- ✅ AI recipe generation (Gemini 2.5 Flash) with mood chips (time, style, mood)

- ✅ Servings scaling

- ✅ Substitution suggestions

- ✅ Leftover mode

- ✅ Recipe deduplication (last 20 titles)

- ✅ Weekly meal planner (7 days, 3 meals/day)

- ✅ Meal plan persistence (Firestore)

- ✅ Shopping list — auto-generated from meal plan, excludes pantry items, includes running low items

- ✅ Hands-free cooking mode (basic — step highlighting, no voice)

- ✅ Recipe rating (thumbs up/down) + adaptive taste profile

- ✅ Household/family profiles with dietary constraint union

- ✅ Crashlytics integration

- ✅ Subscription UI (free tier: 3/day cap, Pro placeholder)

- ✅ Cost estimation per recipe (USD/GBP)

- ✅ API key secured (.env.local + run.ps1)

- ✅ Menu plan: empty day tiles (friendly message instead of crash)

- ✅ Menu plan: fill empty meal slots (↺ button on each slot)

- ✅ Shopping list ← Running Low integration

- ✅ Pantry duplicate guard (onboarding)

## Still To Build

- 🔲 Firebase Analytics (event tracking, screen views)

- 🔲 Custom style input on Generate page

- 🔲 Pantry deduplication — fuzzy matching + cleanup migration

- 🔲 Apple Sign-In (required for App Store)

- 🔲 Email/password auth

- 🔲 Expiry date tracking + alerts

- 🔲 Barcode/receipt scanning

- 🔲 Push notifications (FCM)

- 🔲 Budget mode

- 🔲 In-app purchases (actual payment flow)

- 🔲 Voice control for hands-free cooking

- 🔲 Three-tier persistent inventory (perishables as stored tier)

# Sprint 7.3 — Stabilisation ✅ Complete

| # | Task | Status |
| --- | --- | --- |
| 7.3.1 | Fix Google Sign-In (SHA-1 fingerprint) | ✅ Done |
| 7.3.2 | Fix guest pantry persistence | ✅ Done |
| 7.3.3 | Migrate Gemini 2.0 Flash → 2.5 Flash | ✅ Done |
| 7.3.4 | Bump recipe deduplication list to 20 | ✅ Done |
| 7.3.5 | Set up GitHub Actions CI | ✅ Done |
| 7.3.6 | Branch protection on main | ✅ Done |
| 7.3.7 | Fix .gitignore gaps | ✅ Done |
| 7.3.8 | Add CONTRIBUTING.md | ✅ Done |
| 7.3.9 | Move Gemini API key out of source | ✅ Done |
| 7.3.10 | Fix lint warnings | ✅ Done |

# Sprint 8 — Analytics & Core Polish (Current)

Estimate: ~8–10 hours remaining

| # | Task | Status | Est. |
| --- | --- | --- | --- |
| 8.1 | Firebase Analytics: service + setup | 🔲 Todo | 2 hrs |
| 8.2 | Firebase Analytics: onboarding events | 🔲 Todo | 1 hr |
| 8.3 | Firebase Analytics: core feature events | 🔲 Todo | 2 hrs |
| 8.4 | Firebase Analytics: engagement events | 🔲 Todo | 1 hr |
| 8.5 | Custom style input on Generate page | 🔲 Todo | 2–3 hrs |
| 8.6 | Menu plan: empty day tiles | ✅ Done | — |
| 8.7 | Menu plan: fill empty meal slots | ✅ Already worked | — |
| 8.8 | Pantry deduplication (fuzzy match + migration) | 🔄 Partial | 2 hrs |

## Sprint 8 Analytics Events Detail

### Onboarding Events

| Event | Trigger |
| --- | --- |
| onboarding_started | Welcome screen shown |
| onboarding_step_completed | Each screen completed (param: step name) |
| onboarding_completed | Final screen passed |
| onboarding_abandoned | App closed mid-onboarding (param: last step) |
| sign_in_method | Auth method chosen (google / guest) |

### Core Feature Events

| Event | Trigger |
| --- | --- |
| recipe_generated | Successful generation (params: cuisine, time, mood) |
| recipe_generation_failed | Gemini call failed (param: error type) |
| recipe_saved | User bookmarks a recipe |
| recipe_rated | Thumbs up/down (param: direction) |
| meal_plan_generated | Full weekly plan created |
| meal_plan_day_generated | Single day generated |
| shopping_list_viewed | Shopping list opened |
| shopping_list_shared | List shared |
| pantry_item_added | Item added (param: tier) |
| pantry_item_running_low | Item flagged running low |

### Engagement Events

| Event | Trigger |
| --- | --- |
| cooking_mode_started | User enters hands-free mode |
| cooking_mode_completed | User reaches last step |
| upgrade_prompt_shown | Free tier limit hit |
| upgrade_prompt_dismissed | User dismisses upgrade dialog |

# Sprint 9 — Shopping, Inventory & Auth

Estimate: ~12–15 hours

| # | Task | Est. |
| --- | --- | --- |
| 9.1 | Email/password authentication | 2–3 hrs |
| 9.2 | Running Low → Shopping List (group as Restock section, remove flag on purchase) | 1 hr remaining |
| 9.3 | Expiry date tracking + alerts | 3–4 hrs |
| 9.4 | Three-tier persistent inventory | 2–3 hrs |
| 9.5 | Push notifications (FCM) | 4–5 hrs |

# Sprint 10 — Advanced Features

Estimate: ~16–20 hours

| # | Task | Est. |
| --- | --- | --- |
| 10.1 | Budget mode | 3–4 hrs |
| 10.2 | Barcode scanning | 4–5 hrs |
| 10.3 | Voice control for cooking mode | 4–5 hrs |
| 10.4 | Receipt scanning (Gemini Vision OCR) | 5–6 hrs |

# Sprint 11 — Auth Completion & Payments

Estimate: ~12–16 hours

| # | Task | Est. |
| --- | --- | --- |
| 11.1 | Apple Sign-In (App Store requirement) | 3–4 hrs |
| 11.2 | iOS Push Notifications (APNs) | 2–3 hrs |
| 11.3 | In-app purchases via RevenueCat | 6–8 hrs |

# Sprint 12 — Launch Preparation

Estimate: ~14–18 hours

| # | Task | Est. |
| --- | --- | --- |
| 12.1 | Performance audit + optimisation | 3–4 hrs |
| 12.2 | Security hardening + Firestore rules | 2–3 hrs |
| 12.3 | App Store assets + submission | 4–5 hrs |
| 12.4 | Final regression testing (Android + iOS) | 4–5 hrs |

# Timeline Summary

| Sprint | Focus | Est. Hours Remaining |
| --- | --- | --- |
| Sprint 8 (Current) | Analytics & Core Polish | ~8–10 hrs |
| Sprint 9 | Shopping, Inventory & Auth | ~12–15 hrs |
| Sprint 10 | Advanced Features | ~16–20 hrs |
| Sprint 11 | Auth Completion & Payments | ~12–16 hrs |
| Sprint 12 | Launch Preparation | ~14–18 hrs |
| TOTAL |  | ~62–79 hrs |

# Priority Notes

- Sprint 8 analytics must be in place before user testing — data from day one.

- Sprint 9 email/password auth is platform-agnostic, useful before iOS work.

- Sprint 11 (Apple Sign-In + payments) blocks App Store submission.

- Sprint 10 features are differentiators, not blockers — app is launchable after Sprint 9 on Android.

- Gemini model deprecation (1 June 2026) — resolved. Both services use gemini-2.5-flash with thinking disabled.